## Summary
📊 Allocation Audit Report
Generated: 21 Mar 2026 09:48
Metric | Count
Total Allocations Checked | 200
Allocations with Issues | 7
📅 Date Mismatches | 6
📐 Area Over-Allocated | 2
💰 Rate Mismatches | 2
🚫 Lost Activity Allocs | 0
⚠️ Zero Area Allocs | 0
❌ No Scheduled Date | 0

## All Issues
Alloc ID | Job ID | Farmer | Activity | Plot | Cluster | Mukkadam | Scheduled Date | Allocated Date | Total Area | Allocated Area | Remaining Area | Activity Status | Work Status | Farmer Rate | Alloc Rate | Mukkadam Rate | Issue Type | Issue Detail
330 | 2132 | Ramdas Waman Patil (Rawalgaon) | 1st Subcane (पहिली सबकेन) | Plot 76412 | Rawalgaon,Malegaon | Janardhan Bhoye | 2026-03-24 | 2026-02-24 | 5 | 3.3 | 5 | pending | work_not_started | 1500 | 4000 | 3500 | DATE MISMATCH | DATE MISMATCH: scheduled=2026-03-24 but allocated=2026-02-24
330 | 2132 | Ramdas Waman Patil (Rawalgaon) | 1st Subcane (पहिली सबकेन) | Plot 76412 | Rawalgaon,Malegaon | Janardhan Bhoye | 2026-03-24 | 2026-02-24 | 5 | 3.3 | 5 | pending | work_not_started | 1500 | 4000 | 3500 | RATE MISMATCH | RATE MISMATCH: activity=₹1500.00/ac allocation=₹4000.00/ac
102 | 1756 | Gokul Deshmukh | Pruning (छाटणी) | Plot 76186 | Chikani,Sangamner | Vitthal Pawar | 2026-02-28 | 2026-03-08 | 0.75 | 0.75 | 0 | fully_allocated | completed | 4000 | 4000 | 3500 | DATE MISMATCH | DATE MISMATCH: scheduled=2026-02-28 but allocated=2026-03-08
162 | 1970 | Vaibhav Sadhan Palkhede | Pruning (छाटणी) | Plot 21318 | Pimpalgaon Garudeshwar | Hemraj Waghmare | 2026-03-08 | 2026-03-09 | 3 | 3 | 0 | fully_allocated | completed | 4000 | 4000 | 3500 | DATE MISMATCH | DATE MISMATCH: scheduled=2026-03-08 but allocated=2026-03-09
133 | 1883 | Chaya Dnyaneshwar Pagar | Pruning (छाटणी) | Plot 6574 | Satana,Nashik | Ramesh Pithe | 2026-03-19 | 2026-03-10 | 1.82 | 1 | 0 | fully_allocated | work_not_started | 4000 | 23500 | 3000 | DATE MISMATCH | DATE MISMATCH: scheduled=2026-03-19 but allocated=2026-03-10
133 | 1883 | Chaya Dnyaneshwar Pagar | Pruning (छाटणी) | Plot 6574 | Satana,Nashik | Ramesh Pithe | 2026-03-19 | 2026-03-10 | 1.82 | 1 | 0 | fully_allocated | work_not_started | 4000 | 23500 | 3000 | RATE MISMATCH | RATE MISMATCH: activity=₹4000.00/ac allocation=₹23500.00/ac
121 | 1508 | Krushna Nandkumar Sonawane | Pruning (छाटणी) | Plot 76097 | Patoda,Yeola | Tulshiram Gaikwad | 2026-03-10 | 2026-03-13 | 1.25 | 1.25 | 0 | fully_allocated | completed | 4000 | 4000 | 3000 | DATE MISMATCH | DATE MISMATCH: scheduled=2026-03-10 but allocated=2026-03-13
150 | 2288 | Sumit Ashok Patole | 3rd Round Extra Leaf removal | Plot 76399 | test app | akilesh testing | 2026-03-27 | 2026-03-17 | 0.75 | 1.25 | 0.75 | pending | work_not_started | 2500 | 2500 | 4344 | DATE MISMATCH | DATE MISMATCH: scheduled=2026-03-27 but allocated=2026-03-17
150 | 2288 | Sumit Ashok Patole | 3rd Round Extra Leaf removal | Plot 76399 | test app | akilesh testing | 2026-03-27 | 2026-03-17 | 0.75 | 1.25 | 0.75 | pending | work_not_started | 2500 | 2500 | 4344 | AREA OVERALLOC | AREA OVERALLOC: total=0.75ac allocated=1.25ac (over by 0.50ac)
240 | 1904 | Nivrutti Santu Pagar | Pruning (छाटणी) | Plot 25546 | khadak Ozar,Chandwad | Ramesh Pithe | 2026-03-18 | 2026-03-18 | 0.5 | 1.75 | 0 | fully_allocated | work_not_started | 4000 | 4000 | 3700 | AREA OVERALLOC | AREA OVERALLOC: total=0.50ac allocated=1.75ac (over by 1.25ac)

## Date Mismatches
Alloc ID | Job ID | Farmer | Activity | Plot | Cluster | Mukkadam | Scheduled Date | Allocated Date | Days Diff | Total Area | Allocated Area | Work Status
330 | 2132 | Ramdas Waman Patil (Rawalgaon) | 1st Subcane (पहिली सबकेन) | Plot 76412 | Rawalgaon,Malegaon | Janardhan Bhoye | 2026-03-24 | 2026-02-24 | -28 | 5 | 3.3 | work_not_started
102 | 1756 | Gokul Deshmukh | Pruning (छाटणी) | Plot 76186 | Chikani,Sangamner | Vitthal Pawar | 2026-02-28 | 2026-03-08 | 8 | 0.75 | 0.75 | completed
162 | 1970 | Vaibhav Sadhan Palkhede | Pruning (छाटणी) | Plot 21318 | Pimpalgaon Garudeshwar | Hemraj Waghmare | 2026-03-08 | 2026-03-09 | 1 | 3 | 3 | completed
133 | 1883 | Chaya Dnyaneshwar Pagar | Pruning (छाटणी) | Plot 6574 | Satana,Nashik | Ramesh Pithe | 2026-03-19 | 2026-03-10 | -9 | 1.82 | 1 | work_not_started
121 | 1508 | Krushna Nandkumar Sonawane | Pruning (छाटणी) | Plot 76097 | Patoda,Yeola | Tulshiram Gaikwad | 2026-03-10 | 2026-03-13 | 3 | 1.25 | 1.25 | completed
150 | 2288 | Sumit Ashok Patole | 3rd Round Extra Leaf removal | Plot 76399 | test app | akilesh testing | 2026-03-27 | 2026-03-17 | -10 | 0.75 | 1.25 | work_not_started

## Area Issues
Alloc ID | Job ID | Farmer | Activity | Plot | Cluster | Mukkadam | Total Area | Allocated Area | Over By | Scheduled Date | Allocated Date | Activity Status
150 | 2288 | Sumit Ashok Patole | 3rd Round Extra Leaf removal | Plot 76399 | test app | akilesh testing | 0.75 | 1.25 | 0.5 | 2026-03-27 | 2026-03-17 | pending
240 | 1904 | Nivrutti Santu Pagar | Pruning (छाटणी) | Plot 25546 | khadak Ozar,Chandwad | Ramesh Pithe | 0.5 | 1.75 | 1.25 | 2026-03-18 | 2026-03-18 | fully_allocated