## Summary
📊 Sales Date Performance Report
Generated: 21 Mar 2026 13:49 ¦ Total Analysed: 81
Bucket | Count | % Share | Avg Days Late | Total Area (ac)
✅ On Time (≤ 0d) | 17 | 21.0% | -3.8 | 24.33
🟡 Late 1–7d | 52 | 64.2% | 3.7 | 90.03
🟠 Late 7–15d | 11 | 13.6% | 9.9 | 17.75
🔴 Late 15–30d | 1 | 1.2% | 18 | 0.9
💀 Late 30d+ | 0 | 0.0% | 0 | 0
TOTAL | 81 | 100% | 3.1 | 133.01
PER-CLUSTER BREAKDOWN
Cluster | Total | On Time | Late 1-7d | Late 7-15d | Late 15-30d | Late 30d+ | On Time %
Talegaon | 14 | 3 | 8 | 3 | 0 | 0 | 21.4%
Vadner Bhairav 1 | 10 | 2 | 8 | 0 | 0 | 0 | 20.0%
Dindori | 8 | 2 | 5 | 0 | 1 | 0 | 25.0%
Chikani,Sangamner | 7 | 2 | 2 | 3 | 0 | 0 | 28.6%
khadak Ozar,Chandwad | 7 | 1 | 6 | 0 | 0 | 0 | 14.3%
Pimpalgaon Garudeshwar | 7 | 0 | 6 | 1 | 0 | 0 | 0.0%
Satana,Nashik | 6 | 3 | 3 | 0 | 0 | 0 | 50.0%
test app | 5 | 2 | 3 | 0 | 0 | 0 | 40.0%
Nanegaon,Nashik | 5 | 0 | 2 | 3 | 0 | 0 | 0.0%
Patoda,Yeola | 4 | 0 | 3 | 1 | 0 | 0 | 0.0%
Chandwad | 3 | 1 | 2 | 0 | 0 | 0 | 33.3%
— | 3 | 1 | 2 | 0 | 0 | 0 | 33.3%
Rawalgaon,Malegaon | 1 | 0 | 1 | 0 | 0 | 0 | 0.0%
Sinnar | 1 | 0 | 1 | 0 | 0 | 0 | 0.0%

## On Time (≤ 0d)
✅ On Time (≤ 0d) — 17 jobs (21.0%)
JA ID | Job ID | Farmer | Activity | Plot | Cluster | Scheduled Date | Sales Date | Completed Date | Days Diff | Area (ac)
1056 | 1822 | Arun Bhagwant Dargode | Pruning (छाटणी) | Plot 4539 | Dindori | 2026-02-25 | 2026-02-25 | 2026-02-25 | 0 | 0.5
2657 | 1760 | Shobha Trambakrao Chavan | Pruning (छाटणी) | Plot 41341 | Talegaon | 2026-02-27 | 2026-02-27 | 2026-02-27 | 0 | 3
360 | 1817 | Arun Ashok Chavhan ( Avee Broiler) | Pruning (छाटणी) | Plot 76059 | Chandwad | 2026-02-28 | 2026-02-28 | 2026-02-28 | 0 | 3
381 | 1813 | Anita Kailas Chavan | Pruning (छाटणी) | Plot 25258 | Talegaon | 2026-03-02 | 2026-03-02 | 2026-03-02 | 0 | 0.5
1392 | 2087 | Rohan Shrihari Mogal | Pruning (छाटणी) | Plot 76383 | — | 2026-03-09 | 2026-03-09 | 2026-03-09 | 0 | 1
1526 | 1978 | Ashok Namdev Patil | Pruning (छाटणी) | Plot 63535 | Dindori | 2026-03-09 | 2026-03-09 | 2026-03-09 | 0 | 1.5
3995 | 2355 | akilesh t | Shenda Stopping (शेंडा स्टॉपिंग) 1 | Plot 23452 | test app | 2026-03-20 | 2026-03-20 | 2026-03-20 | 0 | 1
2058 | 878 | Nilesh Keda Chavan (Patil) | Pruning (छाटणी) | Plot 75384 | Satana,Nashik | 2026-02-10 | 2026-02-11 | 2026-02-10 | -1 | 1.13
2805 | 1760 | Shobha Trambakrao Chavan | Pruning (छाटणी) | Plot 76187 | Talegaon | 2026-02-26 | 2026-02-27 | 2026-02-26 | -1 | 3
2306 | 1886 | Seema Ramkrushna Pagar | Pruning (छाटणी) | Plot 36090 | khadak Ozar,Chandwad | 2026-03-05 | 2026-03-08 | 2026-03-05 | -3 | 1
3254 | 2163 | Amol Narayana Nikam | Pruning (छाटणी) | Plot 76578 | Vadner Bhairav 1 | 2026-03-11 | 2026-03-14 | 2026-03-11 | -3 | 1.5
3264 | 2162 | Jagannath Shankar Nikam | Pruning (छाटणी) | Plot 76577 | Vadner Bhairav 1 | 2026-03-11 | 2026-03-14 | 2026-03-11 | -3 | 2
3997 | 2355 | akilesh t | Pruning (छाटणी) 1 | Plot 23452 | test app | 2026-03-17 | 2026-03-20 | 2026-03-17 | -3 | 1
2057 | 877 | Nilesh Keda Chavan (Patil) | Pruning (छाटणी) | Plot 75383 | Satana,Nashik | 2026-02-06 | 2026-02-10 | 2026-02-06 | -4 | 1
2074 | 1201 | Nilesh Keda Chavan (Patil) | Pruning (छाटणी) | Plot 75583 | Satana,Nashik | 2026-02-01 | 2026-02-06 | 2026-02-01 | -5 | 0.7
2293 | 1589 | Madhukar Bhikaji Kadlag | Pruning (छाटणी) | Plot 76130 | Chikani,Sangamner | 2026-03-06 | 2026-03-25 | 2026-03-06 | -19 | 1.5
2155 | 1591 | Dyandev ugale | Pruning (छाटणी) | Plot 76109 | Chikani,Sangamner | 2026-02-28 | 2026-03-23 | 2026-02-28 | -23 | 1

## Late 1–7d
🟡 Late 1–7d — 52 jobs (64.2%)
JA ID | Job ID | Farmer | Activity | Plot | Cluster | Scheduled Date | Sales Date | Completed Date | Days Diff | Area (ac)
2137 | 1774 | Nilesh Dnyaneshwar Chavan | Pruning (छाटणी) | Plot 75364 | Talegaon | 2026-02-26 | 2026-02-19 | 2026-02-26 | 7 | 1.5
3035 | 1988 | Shankar Balkrushna Palkhede | Pruning (छाटणी) | Plot 75461 | Pimpalgaon Garudeshwar | 2026-03-11 | 2026-03-04 | 2026-03-11 | 7 | 2
2801 | 1902 | Santu Bala Pagar | Pruning (छाटणी) | Plot 76222 | khadak Ozar,Chandwad | 2026-03-12 | 2026-03-05 | 2026-03-12 | 7 | 0.9
2150 | 884 | Vikram Chintaman Kapadnis | Pruning (छाटणी) | Plot 75387 | Satana,Nashik | 2026-02-15 | 2026-02-09 | 2026-02-15 | 6 | 2.23
2069 | 1774 | Nilesh Dnyaneshwar Chavan | Pruning (छाटणी) | Plot 75363 | Talegaon | 2026-02-25 | 2026-02-19 | 2026-02-25 | 6 | 2.25
2151 | 1774 | Nilesh Dnyaneshwar Chavan | Pruning (छाटणी) | Plot 75363 | Talegaon | 2026-02-25 | 2026-02-19 | 2026-02-25 | 6 | 1.25
2154 | 1756 | Gokul Deshmukh | Pruning (छाटणी) | Plot 76186 | Chikani,Sangamner | 2026-03-06 | 2026-02-28 | 2026-03-06 | 6 | 0.75
2291 | 1903 | Ratan Shinde | Pruning (छाटणी) | Plot 23501 | Sinnar | 2026-03-08 | 2026-03-02 | 2026-03-08 | 6 | 2.5
2802 | 1885 | Dipak Chindu Shinde | Pruning (छाटणी) | Plot 7704 | khadak Ozar,Chandwad | 2026-03-12 | 2026-03-06 | 2026-03-12 | 6 | 1.25
3037 | 2082 | Eknath Baburao Palkhede | Pruning (छाटणी) | Plot 76313 | Pimpalgaon Garudeshwar | 2026-03-12 | 2026-03-06 | 2026-03-12 | 6 | 1.5
2068 | 1774 | Nilesh Dnyaneshwar Chavan | Pruning (छाटणी) | Plot 75363 | Talegaon | 2026-02-24 | 2026-02-19 | 2026-02-24 | 5 | 1.5
2158 | 1593 | Jaydev Baban Varpe | Pruning (छाटणी) | Plot 791 | Chikani,Sangamner | 2026-03-05 | 2026-02-28 | 2026-03-05 | 5 | 1.75
2301 | 2049 | Dnyaneshwar Sampat Shinde | Pruning (छाटणी) | Plot 2799 | Nanegaon,Nashik | 2026-03-10 | 2026-03-05 | 2026-03-10 | 5 | 1.25
2302 | 2049 | Dnyaneshwar Sampat Shinde | Pruning (छाटणी) | Plot 2798 | Nanegaon,Nashik | 2026-03-10 | 2026-03-05 | 2026-03-10 | 5 | 1.75
3036 | 2082 | Eknath Baburao Palkhede | Pruning (छाटणी) | Plot 1238 | Pimpalgaon Garudeshwar | 2026-03-11 | 2026-03-06 | 2026-03-11 | 5 | 1.25
2803 | 1895 | Bhausaheb Valu Pagar | Pruning (छाटणी) | Plot 21407 | khadak Ozar,Chandwad | 2026-03-12 | 2026-03-07 | 2026-03-12 | 5 | 1.6
3001 | 2092 | Anil Prakash Kad | Pruning (छाटणी) | Plot 76446 | — | 2026-03-12 | 2026-03-07 | 2026-03-12 | 5 | 3.5
2799 | 2032 | Arun Ashok Shinde | Pruning (छाटणी) | Plot 76352 | Vadner Bhairav 1 | 2026-03-13 | 2026-03-08 | 2026-03-13 | 5 | 0.42
3326 | 1998 | Anil Sarode | Pruning (छाटणी) | Plot 76044 | Dindori | 2026-03-14 | 2026-03-09 | 2026-03-14 | 5 | 1
1045 | 872 | Nilesh Keda Chavan (Patil) | Pruning (छाटणी) | Plot 75381 | Satana,Nashik | 2026-02-01 | 2026-01-28 | 2026-02-01 | 4 | 0.63
1047 | 875 | Nilesh Keda Chavan (Patil) | Pruning (छाटणी) | Plot 75382 | Satana,Nashik | 2026-02-02 | 2026-01-29 | 2026-02-02 | 4 | 1.39
3266 | 2133 | Abhijit Jibhau Ahire | Pruning (छाटणी) | Plot 3504 | — | 2026-02-06 | 2026-02-02 | 2026-02-06 | 4 | 4.36
2073 | 1954 | Bhagirathibai Madhukar Nigal | Pruning (छाटणी) | Plot 76285 | Talegaon | 2026-03-04 | 2026-02-28 | 2026-03-04 | 4 | 2
2127 | 1954 | Bhagirathibai Madhukar Nigal | Pruning (छाटणी) | Plot 76284 | Talegaon | 2026-03-04 | 2026-02-28 | 2026-03-04 | 4 | 1.25
978 | 1970 | Vaibhav Sadhan Palkhede | Pruning (छाटणी) | Plot 21318 | Pimpalgaon Garudeshwar | 2026-03-08 | 2026-03-05 | 2026-03-09 | 4 | 3
2289 | 1997 | Yashwant Sukadev Thube | Pruning (छाटणी) | Plot 22609 | Dindori | 2026-03-08 | 2026-03-04 | 2026-03-08 | 4 | 1.75
2290 | 1997 | Yashwant Sukadev Thube | Pruning (छाटणी) | Plot 65719 | Dindori | 2026-03-08 | 2026-03-04 | 2026-03-08 | 4 | 1.75
2798 | 2032 | Arun Ashok Shinde | Pruning (छाटणी) | Plot 76352 | Vadner Bhairav 1 | 2026-03-12 | 2026-03-08 | 2026-03-12 | 4 | 2
2800 | 2088 | Tushar Kishor Nikam | Pruning (छाटणी) | Plot 76434 | Vadner Bhairav 1 | 2026-03-13 | 2026-03-09 | 2026-03-13 | 4 | 1.75
3665 | 2132 | Ramdas Waman Patil (Rawalgaon) | Pruning (छाटणी) | Plot 76413 | Rawalgaon,Malegaon | 2026-02-20 | 2026-02-17 | 2026-02-20 | 3 | 2
3033 | 2097 | Sunil Bhausaheb Palkhede | Pruning (छाटणी) | Plot 1070 | test app | 2026-03-07 | 2026-03-04 | 2026-03-07 | 3 | 2.25
3034 | 2097 | Sunil Bhausaheb Palkhede | Pruning (छाटणी) | Plot 1073 | test app | 2026-03-07 | 2026-03-04 | 2026-03-07 | 3 | 1.25
3258 | 1970 | Vaibhav Sadhan Palkhede | Pruning (छाटणी) | Plot 54051 | Pimpalgaon Garudeshwar | 2026-03-08 | 2026-03-05 | 2026-03-08 | 3 | 1
2310 | 2094 | Ramrao Daulatrao Bhalerao | Pruning (छाटणी) | Plot 23609 | Vadner Bhairav 1 | 2026-03-10 | 2026-03-07 | 2026-03-10 | 3 | 2.25
2312 | 2094 | Ramrao Daulatrao Bhalerao | Pruning (छाटणी) | Plot 23609 | Vadner Bhairav 1 | 2026-03-10 | 2026-03-07 | 2026-03-10 | 3 | 0.25
2132 | 1752 | Pravin Dhopre | Pruning (छाटणी) | Plot 76160 | Patoda,Yeola | 2026-03-01 | 2026-02-27 | 2026-03-01 | 2 | 1
2663 | 1760 | Shobha Trambakrao Chavan | Pruning (छाटणी) | Plot 76189 | Talegaon | 2026-03-01 | 2026-02-27 | 2026-03-01 | 2 | 2
3030 | 1817 | Arun Ashok Chavhan ( Avee Broiler) | Pruning (छाटणी) | Plot 76061 | Chandwad | 2026-03-02 | 2026-02-28 | 2026-03-02 | 2 | 3
3044 | 1734 | Vijay borade | Pruning (छाटणी) | Plot 76159 | Patoda,Yeola | 2026-03-02 | 2026-02-28 | 2026-03-02 | 2 | 1.5
2134 | 1825 | Bhagwan Thombare | Pruning (छाटणी) | Plot 23952 | Patoda,Yeola | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2 | 2.25
2162 | 1988 | Shankar Balkrushna Palkhede | Pruning (छाटणी) | Plot 18262 | Pimpalgaon Garudeshwar | 2026-03-06 | 2026-03-04 | 2026-03-06 | 2 | 2
2309 | 2094 | Ramrao Daulatrao Bhalerao | Pruning (छाटणी) | Plot 23609 | Vadner Bhairav 1 | 2026-03-09 | 2026-03-07 | 2026-03-09 | 2 | 2
2322 | 1978 | Ashok Namdev Patil | Pruning (छाटणी) | Plot 4798 | Dindori | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2 | 0.25
2808 | 1964 | Pratik kailas Nikhade | Pruning (छाटणी) | Plot 76290 | Vadner Bhairav 1 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2 | 0.5
2997 | 1964 | Pratik kailas Nikhade | Pruning (छाटणी) | Plot 76292 | Vadner Bhairav 1 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2 | 1.25
2651 | 1760 | Shobha Trambakrao Chavan | Pruning (छाटणी) | Plot 76188 | Talegaon | 2026-02-28 | 2026-02-27 | 2026-02-28 | 1 | 3
367 | 1817 | Arun Ashok Chavhan ( Avee Broiler) | Pruning (छाटणी) | Plot 76060 | Chandwad | 2026-03-01 | 2026-02-28 | 2026-03-01 | 1 | 5
2305 | 1894 | Bapu Laxman Pagar | Pruning (छाटणी) | Plot 76216 | khadak Ozar,Chandwad | 2026-03-05 | 2026-03-04 | 2026-03-05 | 1 | 1.25
2307 | 1893 | Sanjay Suresh Pagar | Pruning (छाटणी) | Plot 67740 | khadak Ozar,Chandwad | 2026-03-06 | 2026-03-05 | 2026-03-06 | 1 | 2.5
2308 | 1894 | Bapu Laxman Pagar | Cordan Tying (ओलांढे बांधणे) | Plot 76216 | khadak Ozar,Chandwad | 2026-03-06 | 2026-03-05 | 2026-03-06 | 1 | 1.25
2323 | 1978 | Ashok Namdev Patil | Pruning (छाटणी) | Plot 4798 | Dindori | 2026-03-10 | 2026-03-09 | 2026-03-10 | 1 | 1.25
4018 | 2355 | akilesh t | Shoot Selection (विरळणी) 1 | Plot 23452 | test app | 2026-03-21 | 2026-03-20 | 2026-03-21 | 1 | 1

## Late 7–15d
🟠 Late 7–15d — 11 jobs (13.6%)
JA ID | Job ID | Farmer | Activity | Plot | Cluster | Scheduled Date | Sales Date | Completed Date | Days Diff | Area (ac)
2070 | 1774 | Nilesh Dnyaneshwar Chavan | Pruning (छाटणी) | Plot 75363 | Talegaon | 2026-03-03 | 2026-02-19 | 2026-03-03 | 12 | 2
2324 | 1508 | Krushna Nandkumar Sonawane | Pruning (छाटणी) | Plot 76097 | Patoda,Yeola | 2026-03-10 | 2026-03-01 | 2026-03-13 | 12 | 1.25
3003 | 1813 | Anita Kailas Chavan | Pruning (छाटणी) | Plot 25258 | Talegaon | 2026-03-14 | 2026-03-02 | 2026-03-14 | 12 | 2
3456 | 2082 | Eknath Baburao Palkhede | Pruning (छाटणी) | Plot 76312 | Pimpalgaon Garudeshwar | 2026-03-18 | 2026-03-06 | 2026-03-18 | 12 | 1.5
3002 | 1813 | Anita Kailas Chavan | Pruning (छाटणी) | Plot 25258 | Talegaon | 2026-03-13 | 2026-03-02 | 2026-03-13 | 11 | 1.5
2288 | 2038 | Hirabai Keshav Kale | Pruning (छाटणी) | Plot 9161 | Nanegaon,Nashik | 2026-03-09 | 2026-02-28 | 2026-03-09 | 9 | 1.5
2300 | 2038 | Hirabai Keshav Kale | Pruning (छाटणी) | Plot 52825 | Nanegaon,Nashik | 2026-03-09 | 2026-02-28 | 2026-03-09 | 9 | 2
2153 | 1600 | Satish ugale | Pruning (छाटणी) | Plot 76142 | Chikani,Sangamner | 2026-02-28 | 2026-02-20 | 2026-02-28 | 8 | 1
2160 | 1756 | Gokul Deshmukh | Pruning (छाटणी) | Plot 76186 | Chikani,Sangamner | 2026-02-28 | 2026-02-28 | 2026-03-08 | 8 | 0.75
2161 | 1756 | Gokul Deshmukh | Pruning (छाटणी) | Plot 76186 | Chikani,Sangamner | 2026-03-08 | 2026-02-28 | 2026-03-08 | 8 | 1.25
2287 | 2038 | Hirabai Keshav Kale | Pruning (छाटणी) | Plot 9161 | Nanegaon,Nashik | 2026-03-08 | 2026-02-28 | 2026-03-08 | 8 | 3

## Late 15–30d
🔴 Late 15–30d — 1 jobs (1.2%)
JA ID | Job ID | Farmer | Activity | Plot | Cluster | Scheduled Date | Sales Date | Completed Date | Days Diff | Area (ac)
3412 | 2002 | Dhananjay Bhausaheb Jadhav | Pruning (छाटणी) | Plot 7297 | Dindori | 2026-03-18 | 2026-02-28 | 2026-03-18 | 18 | 0.9

## Late 30d+
💀 Late 30d+ — 0 jobs (0.0%)
JA ID | Job ID | Farmer | Activity | Plot | Cluster | Scheduled Date | Sales Date | Completed Date | Days Diff | Area (ac)

## All Data
JA ID | Job ID | Farmer | Activity | Plot | Cluster | Scheduled Date | Sales Date | Completed Date | Days Diff | Area (ac) | Bucket
1056 | 1822 | Arun Bhagwant Dargode | Pruning (छाटणी) | Plot 4539 | Dindori | 2026-02-25 | 2026-02-25 | 2026-02-25 | 0 | 0.5 | On Time (≤ 0d)
2657 | 1760 | Shobha Trambakrao Chavan | Pruning (छाटणी) | Plot 41341 | Talegaon | 2026-02-27 | 2026-02-27 | 2026-02-27 | 0 | 3 | On Time (≤ 0d)
360 | 1817 | Arun Ashok Chavhan ( Avee Broiler) | Pruning (छाटणी) | Plot 76059 | Chandwad | 2026-02-28 | 2026-02-28 | 2026-02-28 | 0 | 3 | On Time (≤ 0d)
381 | 1813 | Anita Kailas Chavan | Pruning (छाटणी) | Plot 25258 | Talegaon | 2026-03-02 | 2026-03-02 | 2026-03-02 | 0 | 0.5 | On Time (≤ 0d)
1392 | 2087 | Rohan Shrihari Mogal | Pruning (छाटणी) | Plot 76383 | — | 2026-03-09 | 2026-03-09 | 2026-03-09 | 0 | 1 | On Time (≤ 0d)
1526 | 1978 | Ashok Namdev Patil | Pruning (छाटणी) | Plot 63535 | Dindori | 2026-03-09 | 2026-03-09 | 2026-03-09 | 0 | 1.5 | On Time (≤ 0d)
3995 | 2355 | akilesh t | Shenda Stopping (शेंडा स्टॉपिंग) 1 | Plot 23452 | test app | 2026-03-20 | 2026-03-20 | 2026-03-20 | 0 | 1 | On Time (≤ 0d)
2058 | 878 | Nilesh Keda Chavan (Patil) | Pruning (छाटणी) | Plot 75384 | Satana,Nashik | 2026-02-10 | 2026-02-11 | 2026-02-10 | -1 | 1.13 | On Time (≤ 0d)
2805 | 1760 | Shobha Trambakrao Chavan | Pruning (छाटणी) | Plot 76187 | Talegaon | 2026-02-26 | 2026-02-27 | 2026-02-26 | -1 | 3 | On Time (≤ 0d)
2306 | 1886 | Seema Ramkrushna Pagar | Pruning (छाटणी) | Plot 36090 | khadak Ozar,Chandwad | 2026-03-05 | 2026-03-08 | 2026-03-05 | -3 | 1 | On Time (≤ 0d)
3254 | 2163 | Amol Narayana Nikam | Pruning (छाटणी) | Plot 76578 | Vadner Bhairav 1 | 2026-03-11 | 2026-03-14 | 2026-03-11 | -3 | 1.5 | On Time (≤ 0d)
3264 | 2162 | Jagannath Shankar Nikam | Pruning (छाटणी) | Plot 76577 | Vadner Bhairav 1 | 2026-03-11 | 2026-03-14 | 2026-03-11 | -3 | 2 | On Time (≤ 0d)
3997 | 2355 | akilesh t | Pruning (छाटणी) 1 | Plot 23452 | test app | 2026-03-17 | 2026-03-20 | 2026-03-17 | -3 | 1 | On Time (≤ 0d)
2057 | 877 | Nilesh Keda Chavan (Patil) | Pruning (छाटणी) | Plot 75383 | Satana,Nashik | 2026-02-06 | 2026-02-10 | 2026-02-06 | -4 | 1 | On Time (≤ 0d)
2074 | 1201 | Nilesh Keda Chavan (Patil) | Pruning (छाटणी) | Plot 75583 | Satana,Nashik | 2026-02-01 | 2026-02-06 | 2026-02-01 | -5 | 0.7 | On Time (≤ 0d)
2293 | 1589 | Madhukar Bhikaji Kadlag | Pruning (छाटणी) | Plot 76130 | Chikani,Sangamner | 2026-03-06 | 2026-03-25 | 2026-03-06 | -19 | 1.5 | On Time (≤ 0d)
2155 | 1591 | Dyandev ugale | Pruning (छाटणी) | Plot 76109 | Chikani,Sangamner | 2026-02-28 | 2026-03-23 | 2026-02-28 | -23 | 1 | On Time (≤ 0d)
2137 | 1774 | Nilesh Dnyaneshwar Chavan | Pruning (छाटणी) | Plot 75364 | Talegaon | 2026-02-26 | 2026-02-19 | 2026-02-26 | 7 | 1.5 | Late 1–7d
3035 | 1988 | Shankar Balkrushna Palkhede | Pruning (छाटणी) | Plot 75461 | Pimpalgaon Garudeshwar | 2026-03-11 | 2026-03-04 | 2026-03-11 | 7 | 2 | Late 1–7d
2801 | 1902 | Santu Bala Pagar | Pruning (छाटणी) | Plot 76222 | khadak Ozar,Chandwad | 2026-03-12 | 2026-03-05 | 2026-03-12 | 7 | 0.9 | Late 1–7d
2150 | 884 | Vikram Chintaman Kapadnis | Pruning (छाटणी) | Plot 75387 | Satana,Nashik | 2026-02-15 | 2026-02-09 | 2026-02-15 | 6 | 2.23 | Late 1–7d
2069 | 1774 | Nilesh Dnyaneshwar Chavan | Pruning (छाटणी) | Plot 75363 | Talegaon | 2026-02-25 | 2026-02-19 | 2026-02-25 | 6 | 2.25 | Late 1–7d
2151 | 1774 | Nilesh Dnyaneshwar Chavan | Pruning (छाटणी) | Plot 75363 | Talegaon | 2026-02-25 | 2026-02-19 | 2026-02-25 | 6 | 1.25 | Late 1–7d
2154 | 1756 | Gokul Deshmukh | Pruning (छाटणी) | Plot 76186 | Chikani,Sangamner | 2026-03-06 | 2026-02-28 | 2026-03-06 | 6 | 0.75 | Late 1–7d
2291 | 1903 | Ratan Shinde | Pruning (छाटणी) | Plot 23501 | Sinnar | 2026-03-08 | 2026-03-02 | 2026-03-08 | 6 | 2.5 | Late 1–7d
2802 | 1885 | Dipak Chindu Shinde | Pruning (छाटणी) | Plot 7704 | khadak Ozar,Chandwad | 2026-03-12 | 2026-03-06 | 2026-03-12 | 6 | 1.25 | Late 1–7d
3037 | 2082 | Eknath Baburao Palkhede | Pruning (छाटणी) | Plot 76313 | Pimpalgaon Garudeshwar | 2026-03-12 | 2026-03-06 | 2026-03-12 | 6 | 1.5 | Late 1–7d
2068 | 1774 | Nilesh Dnyaneshwar Chavan | Pruning (छाटणी) | Plot 75363 | Talegaon | 2026-02-24 | 2026-02-19 | 2026-02-24 | 5 | 1.5 | Late 1–7d
2158 | 1593 | Jaydev Baban Varpe | Pruning (छाटणी) | Plot 791 | Chikani,Sangamner | 2026-03-05 | 2026-02-28 | 2026-03-05 | 5 | 1.75 | Late 1–7d
2301 | 2049 | Dnyaneshwar Sampat Shinde | Pruning (छाटणी) | Plot 2799 | Nanegaon,Nashik | 2026-03-10 | 2026-03-05 | 2026-03-10 | 5 | 1.25 | Late 1–7d
2302 | 2049 | Dnyaneshwar Sampat Shinde | Pruning (छाटणी) | Plot 2798 | Nanegaon,Nashik | 2026-03-10 | 2026-03-05 | 2026-03-10 | 5 | 1.75 | Late 1–7d
3036 | 2082 | Eknath Baburao Palkhede | Pruning (छाटणी) | Plot 1238 | Pimpalgaon Garudeshwar | 2026-03-11 | 2026-03-06 | 2026-03-11 | 5 | 1.25 | Late 1–7d
2803 | 1895 | Bhausaheb Valu Pagar | Pruning (छाटणी) | Plot 21407 | khadak Ozar,Chandwad | 2026-03-12 | 2026-03-07 | 2026-03-12 | 5 | 1.6 | Late 1–7d
3001 | 2092 | Anil Prakash Kad | Pruning (छाटणी) | Plot 76446 | — | 2026-03-12 | 2026-03-07 | 2026-03-12 | 5 | 3.5 | Late 1–7d
2799 | 2032 | Arun Ashok Shinde | Pruning (छाटणी) | Plot 76352 | Vadner Bhairav 1 | 2026-03-13 | 2026-03-08 | 2026-03-13 | 5 | 0.42 | Late 1–7d
3326 | 1998 | Anil Sarode | Pruning (छाटणी) | Plot 76044 | Dindori | 2026-03-14 | 2026-03-09 | 2026-03-14 | 5 | 1 | Late 1–7d
1045 | 872 | Nilesh Keda Chavan (Patil) | Pruning (छाटणी) | Plot 75381 | Satana,Nashik | 2026-02-01 | 2026-01-28 | 2026-02-01 | 4 | 0.63 | Late 1–7d
1047 | 875 | Nilesh Keda Chavan (Patil) | Pruning (छाटणी) | Plot 75382 | Satana,Nashik | 2026-02-02 | 2026-01-29 | 2026-02-02 | 4 | 1.39 | Late 1–7d
3266 | 2133 | Abhijit Jibhau Ahire | Pruning (छाटणी) | Plot 3504 | — | 2026-02-06 | 2026-02-02 | 2026-02-06 | 4 | 4.36 | Late 1–7d
2073 | 1954 | Bhagirathibai Madhukar Nigal | Pruning (छाटणी) | Plot 76285 | Talegaon | 2026-03-04 | 2026-02-28 | 2026-03-04 | 4 | 2 | Late 1–7d
2127 | 1954 | Bhagirathibai Madhukar Nigal | Pruning (छाटणी) | Plot 76284 | Talegaon | 2026-03-04 | 2026-02-28 | 2026-03-04 | 4 | 1.25 | Late 1–7d
978 | 1970 | Vaibhav Sadhan Palkhede | Pruning (छाटणी) | Plot 21318 | Pimpalgaon Garudeshwar | 2026-03-08 | 2026-03-05 | 2026-03-09 | 4 | 3 | Late 1–7d
2289 | 1997 | Yashwant Sukadev Thube | Pruning (छाटणी) | Plot 22609 | Dindori | 2026-03-08 | 2026-03-04 | 2026-03-08 | 4 | 1.75 | Late 1–7d
2290 | 1997 | Yashwant Sukadev Thube | Pruning (छाटणी) | Plot 65719 | Dindori | 2026-03-08 | 2026-03-04 | 2026-03-08 | 4 | 1.75 | Late 1–7d
2798 | 2032 | Arun Ashok Shinde | Pruning (छाटणी) | Plot 76352 | Vadner Bhairav 1 | 2026-03-12 | 2026-03-08 | 2026-03-12 | 4 | 2 | Late 1–7d
2800 | 2088 | Tushar Kishor Nikam | Pruning (छाटणी) | Plot 76434 | Vadner Bhairav 1 | 2026-03-13 | 2026-03-09 | 2026-03-13 | 4 | 1.75 | Late 1–7d
3665 | 2132 | Ramdas Waman Patil (Rawalgaon) | Pruning (छाटणी) | Plot 76413 | Rawalgaon,Malegaon | 2026-02-20 | 2026-02-17 | 2026-02-20 | 3 | 2 | Late 1–7d
3033 | 2097 | Sunil Bhausaheb Palkhede | Pruning (छाटणी) | Plot 1070 | test app | 2026-03-07 | 2026-03-04 | 2026-03-07 | 3 | 2.25 | Late 1–7d
3034 | 2097 | Sunil Bhausaheb Palkhede | Pruning (छाटणी) | Plot 1073 | test app | 2026-03-07 | 2026-03-04 | 2026-03-07 | 3 | 1.25 | Late 1–7d
3258 | 1970 | Vaibhav Sadhan Palkhede | Pruning (छाटणी) | Plot 54051 | Pimpalgaon Garudeshwar | 2026-03-08 | 2026-03-05 | 2026-03-08 | 3 | 1 | Late 1–7d
2310 | 2094 | Ramrao Daulatrao Bhalerao | Pruning (छाटणी) | Plot 23609 | Vadner Bhairav 1 | 2026-03-10 | 2026-03-07 | 2026-03-10 | 3 | 2.25 | Late 1–7d
2312 | 2094 | Ramrao Daulatrao Bhalerao | Pruning (छाटणी) | Plot 23609 | Vadner Bhairav 1 | 2026-03-10 | 2026-03-07 | 2026-03-10 | 3 | 0.25 | Late 1–7d
2132 | 1752 | Pravin Dhopre | Pruning (छाटणी) | Plot 76160 | Patoda,Yeola | 2026-03-01 | 2026-02-27 | 2026-03-01 | 2 | 1 | Late 1–7d
2663 | 1760 | Shobha Trambakrao Chavan | Pruning (छाटणी) | Plot 76189 | Talegaon | 2026-03-01 | 2026-02-27 | 2026-03-01 | 2 | 2 | Late 1–7d
3030 | 1817 | Arun Ashok Chavhan ( Avee Broiler) | Pruning (छाटणी) | Plot 76061 | Chandwad | 2026-03-02 | 2026-02-28 | 2026-03-02 | 2 | 3 | Late 1–7d
3044 | 1734 | Vijay borade | Pruning (छाटणी) | Plot 76159 | Patoda,Yeola | 2026-03-02 | 2026-02-28 | 2026-03-02 | 2 | 1.5 | Late 1–7d
2134 | 1825 | Bhagwan Thombare | Pruning (छाटणी) | Plot 23952 | Patoda,Yeola | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2 | 2.25 | Late 1–7d
2162 | 1988 | Shankar Balkrushna Palkhede | Pruning (छाटणी) | Plot 18262 | Pimpalgaon Garudeshwar | 2026-03-06 | 2026-03-04 | 2026-03-06 | 2 | 2 | Late 1–7d
2309 | 2094 | Ramrao Daulatrao Bhalerao | Pruning (छाटणी) | Plot 23609 | Vadner Bhairav 1 | 2026-03-09 | 2026-03-07 | 2026-03-09 | 2 | 2 | Late 1–7d
2322 | 1978 | Ashok Namdev Patil | Pruning (छाटणी) | Plot 4798 | Dindori | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2 | 0.25 | Late 1–7d
2808 | 1964 | Pratik kailas Nikhade | Pruning (छाटणी) | Plot 76290 | Vadner Bhairav 1 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2 | 0.5 | Late 1–7d
2997 | 1964 | Pratik kailas Nikhade | Pruning (छाटणी) | Plot 76292 | Vadner Bhairav 1 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2 | 1.25 | Late 1–7d
2651 | 1760 | Shobha Trambakrao Chavan | Pruning (छाटणी) | Plot 76188 | Talegaon | 2026-02-28 | 2026-02-27 | 2026-02-28 | 1 | 3 | Late 1–7d
367 | 1817 | Arun Ashok Chavhan ( Avee Broiler) | Pruning (छाटणी) | Plot 76060 | Chandwad | 2026-03-01 | 2026-02-28 | 2026-03-01 | 1 | 5 | Late 1–7d
2305 | 1894 | Bapu Laxman Pagar | Pruning (छाटणी) | Plot 76216 | khadak Ozar,Chandwad | 2026-03-05 | 2026-03-04 | 2026-03-05 | 1 | 1.25 | Late 1–7d
2307 | 1893 | Sanjay Suresh Pagar | Pruning (छाटणी) | Plot 67740 | khadak Ozar,Chandwad | 2026-03-06 | 2026-03-05 | 2026-03-06 | 1 | 2.5 | Late 1–7d
2308 | 1894 | Bapu Laxman Pagar | Cordan Tying (ओलांढे बांधणे) | Plot 76216 | khadak Ozar,Chandwad | 2026-03-06 | 2026-03-05 | 2026-03-06 | 1 | 1.25 | Late 1–7d
2323 | 1978 | Ashok Namdev Patil | Pruning (छाटणी) | Plot 4798 | Dindori | 2026-03-10 | 2026-03-09 | 2026-03-10 | 1 | 1.25 | Late 1–7d
4018 | 2355 | akilesh t | Shoot Selection (विरळणी) 1 | Plot 23452 | test app | 2026-03-21 | 2026-03-20 | 2026-03-21 | 1 | 1 | Late 1–7d
2070 | 1774 | Nilesh Dnyaneshwar Chavan | Pruning (छाटणी) | Plot 75363 | Talegaon | 2026-03-03 | 2026-02-19 | 2026-03-03 | 12 | 2 | Late 7–15d
2324 | 1508 | Krushna Nandkumar Sonawane | Pruning (छाटणी) | Plot 76097 | Patoda,Yeola | 2026-03-10 | 2026-03-01 | 2026-03-13 | 12 | 1.25 | Late 7–15d
3003 | 1813 | Anita Kailas Chavan | Pruning (छाटणी) | Plot 25258 | Talegaon | 2026-03-14 | 2026-03-02 | 2026-03-14 | 12 | 2 | Late 7–15d
3456 | 2082 | Eknath Baburao Palkhede | Pruning (छाटणी) | Plot 76312 | Pimpalgaon Garudeshwar | 2026-03-18 | 2026-03-06 | 2026-03-18 | 12 | 1.5 | Late 7–15d
3002 | 1813 | Anita Kailas Chavan | Pruning (छाटणी) | Plot 25258 | Talegaon | 2026-03-13 | 2026-03-02 | 2026-03-13 | 11 | 1.5 | Late 7–15d
2288 | 2038 | Hirabai Keshav Kale | Pruning (छाटणी) | Plot 9161 | Nanegaon,Nashik | 2026-03-09 | 2026-02-28 | 2026-03-09 | 9 | 1.5 | Late 7–15d
2300 | 2038 | Hirabai Keshav Kale | Pruning (छाटणी) | Plot 52825 | Nanegaon,Nashik | 2026-03-09 | 2026-02-28 | 2026-03-09 | 9 | 2 | Late 7–15d
2153 | 1600 | Satish ugale | Pruning (छाटणी) | Plot 76142 | Chikani,Sangamner | 2026-02-28 | 2026-02-20 | 2026-02-28 | 8 | 1 | Late 7–15d
2160 | 1756 | Gokul Deshmukh | Pruning (छाटणी) | Plot 76186 | Chikani,Sangamner | 2026-02-28 | 2026-02-28 | 2026-03-08 | 8 | 0.75 | Late 7–15d
2161 | 1756 | Gokul Deshmukh | Pruning (छाटणी) | Plot 76186 | Chikani,Sangamner | 2026-03-08 | 2026-02-28 | 2026-03-08 | 8 | 1.25 | Late 7–15d
2287 | 2038 | Hirabai Keshav Kale | Pruning (छाटणी) | Plot 9161 | Nanegaon,Nashik | 2026-03-08 | 2026-02-28 | 2026-03-08 | 8 | 3 | Late 7–15d
3412 | 2002 | Dhananjay Bhausaheb Jadhav | Pruning (छाटणी) | Plot 7297 | Dindori | 2026-03-18 | 2026-02-28 | 2026-03-18 | 18 | 0.9 | Late 15–30d